## Current
Category | ID | Task | Priority | Est. Duration | Details
Planning | 1.1 | Defining Aims & Objectives | High | 3 days | Define a set of aims and objectives to inform the project direction.
Planning | 1.2 | Considering Ethics and Risks | Medium | 1 week | Consider any causes for ethical concern. Document potential risks and appropriate mitigations.
Planning | 1.3 | Work Breakdown + Gantt Chart | Medium | 1 week | Break down and sequence project tasks to produce a Gantt chart of the project schedule.
PDD | 2.1 | Background & Purpose | High | 3 days | Write a section covering the project aims, objectives and scope. Define a set of deliverables.
PDD | 2.2 | Rationale & Operation | Medium | 3 days | Write a section conveying the benefits of the project and how it will be conducted.
PDD | 2.3 | PDD - Supervisor Feedback | Low | 1 day | Ask for feedback on current PDD draft, then make revisions.
PDD | 2.4 | Methodology & Outcomes | Medium | 3 days | Detail an account of how the project will be undertaken in terms of tasks and scheduling.
PDD | 2.5 | Revisions & Miscellany | Low | 3 days | Ensure that the document is well-presented and coherent.
PDD | M-A | PDD Complete | Milestone | 3 weeks | 14th Oct, '24 - The Project Definition Document (PDD) has been completed.
Report | 3.1 | Introduction | Low | 1 week | Write a section introducing the project including it's aims, objectives and context.
Report | 3.2 | Initial Reading & Lit. Search | High | 2 weeks | Conduct a literature search, reading papers and building an overall narrative for the review.
Report | 3.3 | Lit. Review - Metaheuristics | Medium | 3 weeks | Read relevant articles and write about metaheuristics and their applications.
Report | 3.4 | Lit. Review - MSA Approaches | Medium | 3 weeks | Read relevant articles and write about the history of MSA software and approaches.
Report | M-B | Literature Review Complete | Milestone | 5 weeks | 25th Oct, '24 - The literature review has been completed.
Report | 4.1 | Defining Software Requirements | High | 3 days | Capture a discrete set of requirements to direct the design and development of the tool.
Report | 4.2 | Software Design - UML Diagrams | Medium | 3 days | Produce UML diagrams as high-level software design incl. Use Case, Package, Class diagrams.
Category | ID | Task | Priority | Est. Duration | Details
Report | 4.3 | Feedback & Revisions 1 | Low | 2 weeks | Ask for feedback on literature review and design sections, then make revisions.
Report | 4.4 | Technical Background | Low | 2 weeks | Write a section detailing the MSA problem to provide context for other report sections.
Report | 4.5 | Evaluation & Conclusion | High | 2 weeks | Evaluate the project as a whole, including comments on development and software testing.
Report | 4.6 | Feedback & Revisions 2 | Low | 2 weeks | Ask for feedback on technical background and evaluation sections, then make revisions.
Report | M-J | Final Report Complete | Milestone | 6 months | 1st Apr, '25 - The Final Report has been completed, concluding the project.
Development | M-C | Sprint 1 Complete | Milestone | 2 weeks | 12th Nov, '24 - MAli v0.1 is released - a basic tool that produces low quality, but valid solutions for MSA.
Development | M-D | Sprint 2 Complete | Milestone | 2 weeks | 26th Nov, '24 - MAli v0.2 is released - introducing a metaheuristic algorithm to guide the alignment.
Development | M-E | Sprint 3 Complete | Milestone | 2 weeks | 10th Dec, '24 - MAli v1.0 is released - an improvement on v0.2 and indicative of a full implementation.
Development | M-F | Sprint 4 Complete | Milestone | 2 weeks | 14th Jan, '25 - MAli v1.1 is released - resulting from experimentation on the v1.0 design.
Development | M-G | Sprint 5 Complete | Milestone | 2 weeks | 28th Jan, '25 - MAli v1.2 is released - producing a selection of high-quality solutions as output.
Development | M-H | Sprint 6 Complete | Milestone | 2 weeks | 11th Feb, '25 - MAli v1.3 is released - fulfilling all functional and non-functional requirements.
Evaluation | 5.1 | Testing Requirements | High | 1 week | Test defined function & non-functional requirements using a university desktop computer.
Evaluation | 5.2 | Performing Study | Medium | 1 week | Test the software alongside alternatives using structural benchmarking to allow for comparison.
Evaluation | 5.3 | Evaluation & Writeup | Medium | 1 week | Comment on the performance and quality of the developed tool.
Evaluation | M-I | Completed Software Eval. | Milestone | 3 weeks | 4th Mar, '25 - Software requirements have been tested and a case study has been completed.

## Current (2)
Category | ID | Details | Priority | Est. Duration
Planning | 1.1 | Define a set of aims and objectives to inform the project direction. | High | 3 days
Planning | 1.2 | Consider any causes for ethical concern. Document potential risks and appropriate mitigations. | Medium | 1 week
Planning | 1.3 | Break down and sequence project tasks to produce a Gantt chart of the project schedule. | Medium | 1 week
PDD | 2.1 | Write a section covering the project aims, objectives and scope. Define a set of deliverables. | High | 3 days
PDD | 2.2 | Write a section conveying the benefits of the project and how it will be conducted. | Medium | 3 days
PDD | 2.3 | Ask for feedback on current PDD draft, then make revisions. | Low | 1 day
PDD | 2.4 | Detail an account of how the project will be undertaken in terms of tasks and scheduling. | Medium | 3 days
PDD | 2.5 | Ensure that the document is well-presented and coherent. | Low | 3 days
PDD | M-A | 14th Oct, '24 - The Project Definition Document (PDD) has been completed. | Milestone | 3 weeks
Report | 3.1 | Write a section introducing the project including it's aims, objectives and context. | Low | 1 week
Report | 3.2 | Conduct a literature search, reading papers and building an overall narrative for the review. | High | 2 weeks
Report | 3.3 | Read relevant articles and write about metaheuristics and their applications. | Medium | 3 weeks
Report | 3.4 | Read relevant articles and write about the history of MSA software and approaches. | Medium | 3 weeks
Report | M-B | 25th Oct, '24 - The literature review has been completed. | Milestone | 5 weeks
Report | 4.1 | Capture a discrete set of requirements to direct the design and development of the tool. | High | 3 days
Report | 4.2 | Produce UML diagrams as high-level software design incl. Use Case, Package, Class diagrams. | Medium | 3 days
Category | ID | Details | Priority | Est. Duration
Report | 4.3 | Ask for feedback on literature review and design sections, then make revisions. | Low | 2 weeks
Report | 4.4 | Write a section detailing the MSA problem to provide context for other report sections. | Low | 2 weeks
Report | 4.5 | Evaluate the project as a whole, including comments on development and software testing. | High | 2 weeks
Report | 4.6 | Ask for feedback on technical background and evaluation sections, then make revisions. | Low | 2 weeks
Report | M-J | 1st Apr, '25 - The Final Report has been completed, concluding the project. | Milestone | 6 months
Soft. Dev. | M-C | 12th Nov, '24 - MAli v0.1 is released - a basic tool that produces low quality, but valid solutions for MSA. | Milestone | 2 weeks
Soft. Dev. | M-D | 26th Nov, '24 - MAli v0.2 is released - introducing a metaheuristic algorithm to guide the alignment. | Milestone | 2 weeks
Soft. Dev. | M-E | 10th Dec, '24 - MAli v1.0 is released - an improvement on v0.2 and indicative of a full implementation. | Milestone | 2 weeks
Soft. Dev. | M-F | 14th Jan, '25 - MAli v1.1 is released - resulting from experimentation on the v1.0 design. | Milestone | 2 weeks
Soft. Dev. | M-G | 28th Jan, '25 - MAli v1.2 is released - producing a selection of high-quality solutions as output. | Milestone | 2 weeks
Soft. Dev. | M-H | 11th Feb, '25 - MAli v1.3 is released - fulfilling all functional and non-functional requirements. | Milestone | 2 weeks
Evaluation | 5.1 | Test defined function & non-functional requirements using a university desktop computer. | High | 1 week
Evaluation | 5.2 | Test the software alongside alternatives using structural benchmarking to allow for comparison. | Medium | 1 week
Evaluation | 5.3 | Comment on the performance and quality of the developed tool. | Medium | 1 week
Evaluation | M-I | 4th Mar, '25 - Software requirements have been tested and a case study has been completed. | Milestone | 3 weeks