## PDD
#A | #B | Section Title | Word Count (est.) | Draft Completion |  |  | word limit: 2500
1 | 1 | Introduction | 42 | 100% | 90% | 69.69%
1 | 2 | Objectives | 381 | 80%
1 | 3 | Scope | 174 | 80%
1 | 4 | Deliverables | 297 | 80%
1 | 5 | Constraints | 59 | 100% |  |  | the real constraint is use of TC & SP score?
1 | 6 | Assumptions | 108 | 100% |  |  | or say I'm using Sbench bc im not a bioinformatician
2 | 1 | Project Benefits | 125 | 80% | 75%
2 | 2 | Project Operation | 152 | 75%
2 | 3 | Options | 184 | 75%
2 | 4 | Risks Mits | 95 | 75%
2 | 6 | Ethics Legal | 117 | 75%
2 | 7 | Commercial | 136 | 70%
3 | 1 | Initial Project Plan | 45 | 50% | 41.67% |  | refer to rubric! I'm dev + research!
3 | 2 | Project Control | 144 | 75%
3 | 3 | Project Eval | 0 | 0%
4 | 1 | References |  | 0% | 0%
references
write my evaluation
full list of tasks

## RiskMatrix
Likelihood
|  | 1 - Low | 2 - Medium | 3 - High
Severity | 1 - Very Low | 1 | 2 | 3
| 2 - Low | 2 | 4 | 6
| 3 - Medium | 3 | 6 | 9
| 4 - High | 4 | 8 | 12
| 5 - Very High | 5 | 10 | 15

## Maths
Title | Rate | Units | Total Cost
Undergraduate Researcher | £14.00/h | 400 hours | 6400
Project Supervisor - Level 9 | £110.00/h | 20 hours | 2200
GitHub Enterprise | £16.04/mo* | 9 months | 144.36
Visual Studio Enterprise | £190.96/mo* | 9 months | 1718.64
Literature Access Budget | 1200 | -- | 1200
11663
10863
Title | Rate | Quantity | Total Cost
Undergraduate Researcher | £14.00/h | 400 hours | 5600
Project Supervisor - Level 9 | £110.00/h | 20 hours | 2200
GitHub Enterprise | £16.04/mo* | 9 months | 144.36
Visual Studio Enterprise | £190.96/mo* | 9 months | 1718.64
Literature Access Budget | 1200 | -- | 1200
Total Cost |  |  | 10863