## Sheet1
Category | Task | Priority | Est. Duration | Details
Project Planning | Defining Aims & Objectives | High |  | Defining a set of aims and objectives to inform the project direction.
Project Planning | Considering Ethics, Risks & Mitigations | Medium |  | Considering potential causes for ethical concern, documenting
Project Planning | Work Breakdown + Gantt Chart | Medium |  | Breaking down and sequencing project tasks to produce a Gantt chart of the project schedule.
Project Definition Document | Background & Purpose
Project Definition Document | Rationale & Operation
Project Definition Document | PDD - Supervisor Feedback |  | 1 day | Asking for feedback on current PDD draft, then making revisions.
Project Definition Document | Methodology & Outcomes
Project Definition Document | Revisions & Miscellany
Project Definition Document | PDD Complete | Milestone
Final Report | Introduction
Final Report | Initial Reading for Literature Review
Final Report | Literature Review - Metaheuristics
Final Report | Literature Review - Approaches for MSA
Final Report | Literature Review Complete | Milestone
Final Report | Defining Software Requirements
Final Report | Software Design - UML Diagrams |  |  | Producing UML diagrams for high-level software design incl. Use Case, Package, Class diagrams.
Final Report | Feedback & Revisions 1 |  |  | Asking for feedback on literature review and design sections, then making revisions.
Final Report | Technical Background |  |  | A section detailing the MSA problem to provide context for other report sections.
Final Report | Evaluation & Conclusion
Final Report | Feedback & Revisions 2 |  |  | Asking for feedback on technical background and evaluation sections, then making revisions.
Final Report | Final Report Complete | Milestone