## Slide 1: Project planning
Dr P A Robinson
600091 Honours Stage Project

## Slide 2: Planning
“Planning is an unnatural process; it is much more fun to do something. The nicest thing about not planning is that failure comes as a complete surprise, rather than being preceded by a period of worry and depression.”
Sir John Harvey-Jones

## Slide 3: Planning
“In preparing for battle I have always found that plans are useless, but planning is indispensable.”
Dwight D. Eisenhower
“No battle plan ever survived contact with the enemy”
Field Marshal Helmuth von Moltke (the elder)

## Slide 4: Planning
“Those who are victorious plan effectively and change decisively. They are like a great river that maintains its course but adjusts its flow.”
Sun Tzu

## Slide 5: Aims and objectives
Aims
  High level targets
  What the project as a whole will try to do
  Expresses desired outcome
Objectives
  More detailed and specific items
  Easy to determine if complete/successful
  Primary and secondary objectives
    Not too many!

## Slide 6: Objectives
Objectives must be SMART:
Specific
  Is the objective well defined and clear? Can it be understood by anyone with basic knowledge of the project?
Measurable
  Can you measure progress towards the objective? How will you know when it is complete?
Appropriate
  Does the objective fit with and contribute to the overall aims of the project? Has it been agreed by all?
Realistic
  Within the resource constraints of the project, can this goal be achieved?
Time-based
  When will the goal be completed? Is there enough time to achieve the goal? Is there too much time (consider Parkinson’s law).

## Slide 7: Creating a cunning plan
Work breakdown
Time estimates
Identifying milestones
Sequencing activities
Scheduling
Replanning
Using the right tools

## Slide 8: Mind map

## Slide 9: Work breakdown
Face Recognition DL project
Literature survey
Develop DL model
Get training data
Evaluation
Complete report
Literature search
Literature review
Train DL model
Use other models
Analyse results
Review tests
Analyse / evaluate
User feedback
Analyse user feedback
Propose changes
Investigate DL models
Design DL system
Develop and test DL System
Estimate time for lowest level tasks

## Slide 10: Work breakdown
Face Recognition DL project
Get training data
Evaluation
Complete report
Develop DL model
Literature survey
Literature search
User feedback
Use other models
Analyse results
Analyse user feedback
Propose changes
Review tests
Analyse / evaluate
Investigate DL models
Design DL system
Develop and test DL System
Estimate time for lowest level tasks
Literature review
Train DL model

## Slide 11: Work breakdown
Face Recognition DL project
Literature survey
Develop DL model
Get training data
Evaluation
Complete report
Literature search
Literature review
Train DL model
Use other models
Analyse results
Review tests
Analyse / evaluate
User feedback
Analyse user feedback
Propose changes
Investigate DL models
Design DL system
Develop and test DL System
Estimate time for lowest level tasks

## Slide 12: Time estimates
Activity | Time (weeks)
Literature search | 8
Literature review | 4
Investigate DL models | 4
Design DL system | 4
Develop and test DL system | 2
Get training data | 1
Train DL model | 1
Use other models | 2
Review tests | 2
Analyse/evaluate | 4
Analyse user feedback | 2
Complete report | 8
Total effort | 42

## Slide 13: Not enough time?
You have an end date (Week 11 of semester 2)
Work backwards
Adjust the scope of the project to fit the time?
  Better than running out of time at the end
Adjust the balance of time between components?
Improve estimates by more detailed breakdown?
Be realistic!
Remember there’s an interim review in January

## Slide 14: Identify milestones
Intermediate goals to help measure progress
  Focus points for effort
May be deliverables
  Project completion is always one!
What should they be?
  May be project objectives
  Literature review? DL model? Final report?
How many?
  Depends on project length. Five or six?

## Slide 15: Sequencing activities
Get training data
Literature search
Analyse user feedback
Investigate DL models
Literature review
1
Use other models
Design DL system
Develop and test DL System
Train DL model
Review tests
Analyse / evaluate
Propose changes
Complete report
2

## Slide 16: Sequencing activities
Get training data
Complete report
Literature search
Literature review
Train DL model
Use other models
Review tests
Analyse / evaluate
Analyse user feedback
Propose changes
Investigate DL models
Design DL system
Develop and test DL System
1
2

## Slide 17: Sequencing activities
Get training data
Complete report
Literature search
Literature review
Train DL model
Use other models
Review tests
Analyse / evaluate
Analyse user feedback
Propose changes
Investigate DL models
Design DL system
Develop and test DL System
1
2
Shows dependencies
Indicates critical activities and path
  (only if timings included)
  And shows up problems?
Can tasks be done in parallel?

## Slide 18: But what are my tasks?
Depends on your project
There are some common tasks (from a scheduling perspective):
  Literature review (deliverable?)
  Requirements capture
  Requirements specification (milestone?)
  Software/hardware design (deliverable?)
  Implementation
    Subtasks depending on project
    Include sprints and other ceremonies
    Include deliverables or milestones for prototypes

## Slide 19: What? There are more?
Experiments and testing
  Don’t forget to include time after these to make changes
Evaluation
  User evaluation of product
    Requires time to plan, prepare, implement and consider the results
    And time to make changes if appropriate
  Self-evaluation of project (reflection)
Writing the report
  Schedule time for writing, feedback and corrections
Don’t forget to include holidays!
  Don’t assume you will work over the Christmas break

## Slide 20: Scheduling – Gantt charts
Use the right tools for the job
Microsoft Project
  Available on university image
Project Libre
  Free download
Please don't use Excel. Or Word.

## Slide 21: MSP demo

## Slide 22: Gantt chart

## Slide 23: Agile planning
I’m doing agile development! I don’t need a plan!
Yes, you do.
  Though it may be less detailed
  When will you do your sprints?
  When will you deliver incremental versions?
  When will you do testing? Research? Report writing…
Agile is not an excuse for chaos

## Slide 24: MSP agile Gantt

## Slide 25: USE the plan!
Make sure you are doing what you should be
Are you falling behind?
Keep it up to date
  Update progress on tasks
Change the plan over time
  Add detail as time goes on
  Mid-way progress report is a good time to replan

## Slide 26: Methodologies
Waterfall?
Spiral?
Incremental?
Prototyping?
Agile?
Which one is most appropriate for your project?
Choose one
Stick with it
Actually do it

## Slide 27: Helpful advice
Keep a log – You’ll be glad you did
  Look at Obsidian, or Notable, or others
Use referencing software
  Endnote, Zotero…
  You’ll be very glad you did
Use source control
  Git and GitHub
Use the right tools for the job
  MS Project
  Freeplane

## Slide 28: Questions?