## Sheet1
Category | ID | Task | Priority | Est. Duration | Details
Planning | 1.1 | Defining Aims & Objectives | High | 3 days | Defining a set of aims and objectives to inform the project direction.
Planning | 1.2 | Considering Ethics, Risks & Mitigations | Medium | 1 week | Considering potential causes for ethical concern, documenting
Planning | 1.3 | Work Breakdown + Gantt Chart | Medium | 1 week | Breaking down and sequencing project tasks to produce a Gantt chart of the project schedule.
PDD | 2.1 | Background & Purpose | High | 3 days
PDD | 2.2 | Rationale & Operation | Medium | 3 days
PDD | 2.3 | PDD - Supervisor Feedback | Low | 1 day | Asking for feedback on current PDD draft, then making revisions.
PDD | 2.4 | Methodology & Outcomes | Medium | 3 days
PDD | 2.5 | Revisions & Miscellany | Low | 3 days
PDD | M-A | PDD Complete | Milestone | 3 weeks | 14th Oct, '24 - The Project Definition Document (PDD) has been completed.
Report | 3.1 | Introduction | Low | 1 week
Report | 3.2 | Initial Reading for Literature Review | High | 2 weeks
Report | 3.3 | Literature Review - Metaheuristics | Medium | 3 weeks
Report | 3.4 | Literature Review - Approaches for MSA | Medium | 3 weeks
Report | M-B | Literature Review Complete | Milestone | 5 weeks | 25th Oct, '24 - The literature review has been completed.
Report | 4.1 | Defining Software Requirements | High | 3 days
Report | 4.2 | Software Design - UML Diagrams | Medium | 3 days | Producing UML diagrams for high-level software design incl. Use Case, Package, Class diagrams.
Category | ID | Task | Priority | Est. Duration | Details
Report | 4.3 | Feedback & Revisions 1 | Low | 2 weeks | Asking for feedback on literature review and design sections, then making revisions.
Report | 4.4 | Technical Background | Low | 2 weeks | A section detailing the MSA problem to provide context for other report sections.
Report | 4.5 | Evaluation & Conclusion | High | 2 weeks | An evaluation of the project as a whole, follows all development sprints and software evaluation tasks.
Report | 4.6 | Feedback & Revisions 2 | Low | 2 weeks | Asking for feedback on technical background and evaluation sections, then making revisions.
Report | M-J | Final Report Complete | Milestone | 6 months | 1st Apr, '25 - The Final Report has been completed, concluding the project.
Development | M-C | Sprint 1 Complete | Milestone | 2 weeks | 12th Nov, '24 - MAli v0.1 is released - write about this
Development | M-D | Sprint 2 Complete | Milestone | 2 weeks | 26th Nov, '24 - MAli v0.2 is released - write about this
Development | M-E | Sprint 3 Complete | Milestone | 2 weeks | 10th Dec, '24 - MAli v1.0 is released - write about this
Development | M-F | Sprint 4 Complete | Milestone | 2 weeks | 14th Jan, '25 - MAli v1.1 is released - write about this
Development | M-G | Sprint 5 Complete | Milestone | 2 weeks | 28th Jan, '25 - MAli v1.2 is released - write about this
Development | M-H | Sprint 6 Complete | Milestone | 2 weeks | 11th Feb, '25 - MAli v1.3 is released - write about this
Evaluation | 5.1 | Testing Requirements (FRs & NFRs) | High | 1 week | The requirements defined in 4.1 are tested using a university desktop computer.
Evaluation | 5.2 | Performing Study | Medium | 1 week | The software is tested alongside alternatives using structural benchmarking to allow for comparison.
Evaluation | 5.3 | Evaluation & Writeup | Medium | 1 week | The results of 5.2 are used to comment on the performance and quality of the developed tool.
Evaluation | M-I | Completed Software Evaluation | Milestone | 3 weeks | 4th Mar, '25 - Software requirements have been tested and a case study has been completed.